## Sheet1
Team Members | Name
Project Manager | Cary |  | Project Start Date: 08.17.2020
Content Creator-Copywriter | Humphrey |  | Project End Date = Start date + 106 days
Web-Designer-Photographer | Audrey
Web-Developer Front-End | Ane
Web-Developer Back-End | Kathrine
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [7 empty] | Week 15
Tasks | Name | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106
Information Gathering - 14 days
Information Gathering |  | 14
Stakeholder Intake Meeting | All | 7
Nice to Haves-Must Haves/Needs Assessment | All | 2
Define Target Audience | All | 1
Create Functional Spec - User Stories | All | 4 | [14 empty] | Content Strategy - 14 days
Content Strategy |  | 14
Design & Branding Meeting | All | 1
Sitemap & Style Tiles | All/Audrey/Ane | 6
Create Technical Spec - Site architectural design | Ane/Kathrine | 4
Define CMS-Hardware-Software Needs | Ane/Kathrine | 4 | [28 empty] | Budget & Resource Planning - 10 days
Budgeting & Resource Planning |  | 10
Budgeting & Resource Planning | Cary | 4
Awaiting Budget/Payment Plan approval |  | 6 | [38 empty] | Content Creation - 30 days
Content Creation |  | 30
Content texts, articles, info, descriptions, copywrite etc | Humphrey | 20
Website Images & Product Images | Audrey | 20
Additional Design Elements (glyphs, textures, shapes etc) | Audrey | 10
Development Framework - validation & forms | Ane | 15
Website Security - Protection of Intellectual Property | Ane/Kathrine | 5
Certificates | Ane/Kathrine | 5 | [68 empty] | Main Review & Test-Phase - 28 days
Review & Testing |  | 28
Review | All | 3
Test-phase | All | 10
Review | All | 3
SEO-Optimization | Humphrey/Ane | 8
Load speed Optimization | Ane/Kathrine | 4 | [96 empty] | Implementation - Launch - 10 days
Implementation |  | 10
Final Review | Ane/Kathrine | 2
Installation and going live | Ane/Kathrine | 8
| Total Days | 106
Team Members | Name | [16 empty] | PROJECT GANTT Chart - if Brand Identity Creation is needed
Project Manager | Cary |  | Project Start Date: 08.17.2020
Content Creator-Copywriter | Humphrey |  | Project End Date = Start date + 140 days
Web-Designer-Photographer | Audrey
Web-Developer Front-End | Ane
Web-Developer Back-End | Kathrine
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [7 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20
Tasks | Name | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141
Information Gathering - 16 days
Information Gathering |  | 16
Stakeholder Intake Meeting | All | 7
Nice to Haves-Must Haves/Needs Assessment | All | 3
Define Target Audience | All | 2
Create Functional Spec - User Stories | All | 4 | [16 empty] | Content Strategy - 36 days
Content Strategy |  | 36
Design & Branding Meeting | All | 2
Building Brand Identity | Humphrey/Audrey/Ane | 14
Sitemap & Style Tiles | All/Audrey/Ane | 8
Create Technical Spec - Site architectural design | Ane/Kathrine | 6
Define CMS-Hardware-Software Needs | Ane/Kathrine | 6 | [52 empty] | Budget & Resource Planning - 10 days
Budgeting & Resource Planning |  | 10
Budgeting & Resource Planning | Cary | 4
Awaiting Budget/Payment Plan approval |  | 6 | [62 empty] | Content Creation - 40 days
Content Creation |  | 40
Content texts, articles, info, descriptions, copywrite etc | Humphrey | 25
Website Images & Product Images | Audrey | 25
Additional Design Elements (glyphs, textures, shapes etc) | Audrey | 10
Development Framework - validation & forms | Ane | 15
Website Security - Protection of Intellectual Property | Ane/Kathrine | 5
Certificates | Ane/Kathrine | 5 | [102 empty] | Main Review & Test-Phase - 28 days
Review & Testing |  | 28
Review | All | 3
Test-phase | All | 10
Review | All | 3
SEO-Optimization | Humphrey/Ane | 8
Load speed Optimization | Ane/Kathrine | 4 | [130 empty] | Implementation - Launch - 10 days
Implementation |  | 10
Final Review | Ane/Kathrine | 2
Installation and going live | Ane/Kathrine | 8
| Total Days | 140